## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Cloud Computing
INTERN NAME: | Pranit Jejurikar
PROJECT NAME: | Automated MongoDB Backup and Recovery System on AWS
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2026-06-08
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Automated MongoDB Backup and Recovery System on AWS |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER
PROJECT SPONSOR
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2026-05-31 | MongoDB collections were not visible after switching databases. | Technical | Yes | Verify database names and collections before querying. | Used show dbs and show collections to identify correct database. | Pranit Jejurikar | Solved | Database naming confusion resolved.
2 | 2026-05-31 | Backup script file could not be located initially. | Configuration | Yes | Maintain a dedicated scripts directory. | Located script using Linux commands and verified file path. | Pranit Jejurikar | Solved | Improved file organization.
3 | 2026-06-03 | Backup restore failed due to duplicate key errors. | Testing | Yes | Remove existing data or use --drop option during restore. | Used mongorestore --drop to overwrite existing collections. | Pranit Jejurikar | Solved | Restore completed successfully afterwards.
4 | 2026-06-05 | Cron job configuration required verification to ensure automation. | Automation | Yes | Test scheduled jobs before deployment. | Verified cron entries using crontab -l and monitored backup generation. | Pranit Jejurikar | Solved | Automated backups worked correctly.
5 | 2026-06-05 | Need to validate backup availability in Amazon S3. | Cloud Storage | Yes | Regularly verify uploaded backup archives. | Used AWS CLI commands to confirm backup files in S3 bucket. | Pranit Jejurikar | Solved | Backup retention verified successfully.
6 | 2026-06-07 | Creating raw database text dumps during implementation risked consuming excessive local disk storage and driving up AWS cloud storage costs as data scales. | Technical / Infrastructure | yes | Leverage native database compression flags within backup utilities to optimize file footprints before transmission | Implemented the native --gzip compression flag directly into the active backup command string within the script execution | Pranit Jejurikar | Solved | Storage optimization successfully minimized local EC2 disk utilization and lowered cloud retention overhead.