## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Automated MongoDB Backup and Recovery System on AWS
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2026-04-30
EXPECTED COMPLETION DATE | 2026-05-07
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To design and implement an automated MongoDB backup and recovery solution using AWS services that creates scheduled backups, stores them securely in Amazon S3, and restores data whenever required.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Manual database backups are time-consuming and vulnerable to human error. An automated backup and recovery solution improves data protection, reduces operational effort, and ensures business continuity during data loss incidents.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | • Automate MongoDB backups. • Upload backups to Amazon S3. • Schedule backups using Cron. • Successfully restore backup data. • Reduce manual intervention. • Improve disaster recovery readiness.
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | • Configured AWS EC2 Instance • MongoDB Database • Amazon S3 Bucket • Backup Automation Script • Cron Scheduler Configuration • Backup and Restore Demonstration • Project Documentation • Demo Video
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | • MongoDB installation • AWS EC2 setup • Amazon S3 integration • AWS CLI configuration • Backup script creation • Scheduled backup execution • Backup restoration • Logging and verification
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | • Multi-region backup replication • Backup encryption • Email notifications • Backup retention policy automation • High availability clustering • Production-scale deployment
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | 1 Intern Developer
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | • Cloud Computing Mentor • AWS Documentation • MongoDB Documentation • Linux Ubuntu Server • AWS EC2 • Amazon S3
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | AWS Free Tier resources were used. No additional project cost was incurred.
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Cloud Counselage Pvt. Ltd.
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | • Cloud Counselage • Domain Mentor • Project Reviewer • Database Administrator • System Administrator
END CUSTOMER (Mention the client name.) | Cloud Counselage Pvt. Ltd.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | • AWS service interruption • Network connectivity issues • Backup corruption • Insufficient storage • Incorrect AWS CLI configuration
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | • AWS services are available. • MongoDB service is running. • Internet connectivity exists. • S3 bucket is accessible. • Required permissions are configured.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | • AWS Free Tier limitations • Limited project duration • Storage limitations • Dependency on internet connectivity
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | Requirement Gathering : 05-07-26
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | Planning : 05-14-26
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | Design : 05-21-26
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | Development : 05-31-26
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | Testing : 06-03-26
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | Deployment : 06-05-26
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | Closure : 06-07-26