## Guide
IAC GLOBAL PROFESSIONAL INTERNSHIP
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Manthan Chaudhary
Document Created On: | 2026-05-15
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop

## Project Schedule
IAC Internship Progra 2023 - <DOMAIN NAME> Project Schedule
|  | PROJECT START DATE | 2026-04-30 | (Enter the date you started working on your project)
|  | Display Week Sr No | 1 | [10 empty] | 2026-04-27 | [6 empty] | 2026-05-04 | [6 empty] | 2026-05-11 | [6 empty] | 2026-05-18 | [6 empty] | 2026-05-25 | [6 empty] | 2026-06-01 | [6 empty] | 2026-06-08 | [6 empty] | 2026-06-15 | [6 empty] | 2026-06-22
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | time axis 2026-04-27 to 2026-06-28
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2026-04-27 to 2026-06-28
1 | [Week title Eg: Pre IP]
1.1 |  | Project Planning | • Understand problem statement • Study MongoDB backup concepts • Study AWS EC2 and S3 • Define project objectives | Requirement gathering, Technology research | None | Pranit jejurikar | 2026-04-30 | 2026-05-14 | 2026-05-14 | 7 | Completed | 100 | Completed Successfully
1.1.1 |  | AWS Environment Setup | • Launch EC2 instance • Install MongoDB • Configure AWS CLI • Create S3 bucket | Launch EC2, Install MongoDB, Create S3 Bucket, Configure AWS CLI | Project Planning | Pranit jejurikar | 2026-05-15 | 2026-05-21 | 2026-05-21 | 6 | Completed | 100 | Completed Successfully
1.1.2 |  | Backup Automation Development | • Create backup script • Configure mongodump • Upload backups to S3 • Create logging mechanism | Create backup script, Configure mongodump, S3 upload | AWS Environment Setup | Pranit jejurikar | 2026-05-22 | 2026-05-31 | 2026-05-31 | 9 | Completed | 100 | Completed Successfully
1.1.3 |  | Cron Scheduler Configuration | • Configure Cron job • Test scheduled execution • Verify backup generation | Create cron job, Test automatic execution | Backup Automation Development | Pranit jejurikar | 2026-05-22 | 2026-05-31 | 2026-05-31 | 8 | Completed | 100 | Completed Successfully
1.1.4 |  | Backup and Restore Testing | • Verify S3 backup files • Download backup archive • Restore using mongorestore • Validate restored data | Verify backups, Download archive, Restore database, Validate data | Cron Scheduler Configuration | Pranit jejurikar | 2026-06-01 | 2026-06-03 | 2026-06-03 | 7 | Completed | 100 | Completed Successfully
1.2 |  | Project Documentation | • Prepare RAID Log • Prepare SRS • Prepare SDS • Prepare Project Report • Prepare Project Charter • Prepare Demo Video | Prepare RAID Log, SRS, SDS, Project Report, Project Charter, Demo Video | Backup and Restore Testing | Pranit jejurikar | 2026-06-04 | 2026-06-07 | 2026-06-07 | 9 | Completed | 100 | Completed Successfully
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you