## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 4 | 1 | 1 | 1 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Automated MongoDB Backup and Recovery System on AWS |  | Project Id: |  | Project Manager: | Harshada Topale |  |  | Assumption | 2 | 0 | 0 | 1 | 1 | 0
[10 empty] | Issue | 3 | 0 | 1 | 1 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2026-06-05 | Project Team Lead: | Domain Lead |  |  | Dependency | 3 | 0 | 2 | 1 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 12 |  |  |  |  | 10
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | AWS Free Tier limits may restrict storage or service usage | Backup storage or testing activities may be affected | Monitor AWS usage regularly and optimize storage consumption | Pranit jejurikar | High | 4 | Open | Risk
2 | Risk | Backup script may fail due to configuration errors. | Scheduled backups may not be generated. | Perform testing and maintain execution logs. | Pranit jejurikar | Critical | 5 | Open | Assumption
3 | Risk | Network connectivity issues during backup upload | Backup files may not reach Amazon S3. | Implement retry mechanism and monitor logs | Pranit jejurikar | Moderate | 3 | Open | Issue
4 | Assumption | AWS services will remain available throughout project execution | Project implementation depends on cloud service availability | Monitor AWS service health dashboard | Pranit jejurikar | Low | 2 | Open | Dependency
5 | Assumption | MongoDB will be installed and configured correctly | Backup automation requires a functioning database | Verify installation before development begins | Pranit jejurikar | Moderate | 3 | Open
6 | Issue | Learning curve for AWS and MongoDB tools | May increase implementation time | Use documentation and tutorials for guidance | Pranit jejurikar | Moderate | 3 | Open | Open
7 | Issue | Limited internship duration | Reduced time for advanced features | Focus on core backup and restore functionality | Pranit jejurikar | High | 4 | Open | Closed
8 | Dependency | Amazon S3 bucket configuration | Backups cannot be stored without S3 access | Configure and test S3 before deployment | Pranit jejurikar | High | 4 | Open
9 | Dependency | AWS CLI installation and authentication | Backup upload process depends on AWS CLI | Configure credentials and validate connection | Pranit jejurikar | High | 4 | Open | Critical
10 | Dependency | Cron Scheduler availability | Automation depends on scheduled execution | Test Cron jobs before final deployment | Pranit jejurikar | Moderate | 3 | Open | High
11 | Risk | Duplicate records during database restore | Restore operation may fail with duplicate key errors | Use mongorestore --drop to replace existing collections | Pranit jejurikar | Moderate | 3 | Closed | Moderate
12 | Issue | Every time the Ubuntu EC2 instance is stopped and restarted to save AWS Free Tier credits, AWS dynamically reassigns a brand new Public IP address. This invalidates existing SSH sessions and local configurations | Loss of operational connectivity to the terminal application, halting command-line administration and verification scripts until manually reconfigured. | Bypassed reliance on desktop terminal clients by leveraging the web-native AWS EC2 Instance Connect dashboard terminal wrapper, ensuring direct root-level access regardless of dynamic IP reassignments. | Pranit jejurikar | Moderate |  | Closed | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24